## Guidance
Purpose
The CWS-CARES Baseline Go-Live Communications Plan is meant to be suggestions for communications and timing that Organizations should consider when creating their Communications plan to create transparency and visibility into stakeholder engagement.
Approach
The Organization OCM Team should review Implementation OCM Team planned communications, phases, and key messages, and identify areas where Organizational nuance may be best addressed by Organization specific communications. As Organizations evaluate their stakeholder engagement, additional communications may be needed at an Organizational level and should also be captured here.
Next Steps
Organization ILs: Partner with your OCM Lead(s) and OCM Team to identify Organization communication needs and begin planning additional and upcoming communications within the document.

## Communication Tracker
Communication Phase | Target Month for Distribution | Communication Topic | Communication Description | Communication Type | Owner | Audience | Recommended Channel
Readiness and Cutover | 2026-09-01 | The Case for Change | Reinforce the vision behind the CWS-CARES implementation, sharing the core problems being solved and the long-term benefits. | Email |  | Organization members
Readiness and Cutover | 2026-09-01 | Instructor-Led Training | Explain or reinforce Instructor-Led training requirements, best practices, and logistics (e.g., CACWT registration, encourage On Demand Learning Enablement Modules, schedules). | Email/Meeting |  | Organization members
Readiness and Cutover | 2026-09-01 | Journey Map | Outline the high-level timeline, key dates that are critical for action prior to Go-Live. | Email/Article |  | Organization members
Readiness and Cutover | 2026-09-01 | Organization 'Day in the Life' Impacts | Leveraging Change Impacts to highlight workflow specific changes. Helps to translate broad CWS-CARES impacts into practical, concrete guides | Tailored Emails |  | Organization members
Readiness and Cutover | 2026-09-01 | Organization Team Deep Dives | Present the specific process changes to individual teams or departments to address localized questions. | Tailored Meetings |  | Organization members
Go-Live and Support | 2026-10-01 | Training Deadlines | Reinforce training completion, highlighting deadlines, offer additional support, and share/celebrate completion rates and achievements. | Tailored Emails |  | Organization members
Go-Live and Support | 2026-10-01 | Super User Q&A | Reinforce channels where users can get support, highlighting Super Users as a peer-to-peer resource. Feature system tips and demos. | Meeting |  | Organization members
Go-Live and Support | 2026-10-01 | Day-One Checklists & QRGs | Distribute Day-One readiness checklists and Quick Reference Guides (QRGs) for employees to have clear instructions. | Articles |  | Organization members
Go-Live and Support | 2026-10-01 | Last Action Items | Highlight a final checklist for employees that must be cleared before Go-Live. | Tailored Emails |  | Organization members
Go-Live and Support | 2026-10-01 | Support & Hypercare Plan | Shares step-by-step instructions on where to go for help. | Email |  | Organization members
Go-Live and Support | 2026-10-01 | We are Live! | Confirms CWS-CARES is officially live. Provides direct, active login links, immediate "First Login" steps, and a celebratory message. | Email |  | Organization members
Go-Live and Support | 2026-11-01 | Daily Support & Issue Highlights | Provides daily or bi-weekly updates on known bugs, temporary workarounds, and resolved issues. | Email |  | Organization members
Go-Live and Support | 2026-11-01 | Training Reminders & Upskilling | Targets individuals who have still not completed training or need refresher sessions via On Demand Learning Enablement Modules. | Tailored Emails |  | Organization members
Go-Live and Support | 2026-11-01 | System Best Practices & "Pro-Tips" | Share short practical guides or video snippets showing shortcuts, tips, and tricks to improve user efficiency. | Articles |  | Organization members
Go-Live and Support | 2026-11-01 | Celebration & Transition to BAU Support | Officially marks the end of post-go-live support. Celebrates the launch, thanks Super Users and OCM Coordinators, and outlines the permanent Business As Usual (BAU) support paths. | Email |  | Organization members