## Guidance
Purpose
The CWS-CARES Stakeholder Registry is meant to serve as a repository for identified stakeholders within the CWS-CARES landscape and serve as a starting point for Organizations beginning their stakeholder analysis.
Approach
The Organization OCM Team should review the CWS-CARES Stakeholder Registry and update instances in identified stakeholders where impact or influence may differ within their Organization and identify additional stakeholder(s) based on the unique circumstances of their Organization.
Next Steps
Organization ILs: Partner with your OCM Lead(s) and OCM Team to review the Stakeholder Registry and make the appropriate updates for your Organizations needs.

## Stakeholder Registry
Stakeholder Group or Individual | Organization | Title |  |  | Stakeholder Observations
|  |  | Current State (Unaware, Aware, Understanding, Buy-In, Commitment) | Desired State (Not aware, Aware, Understanding, Buy-In, Commitment) | Influence (ability of a stakeholder to affect or impact the change or decisions) (High, Medium, Low, No Impact) | Impact (extent to which a stakeholder is affected by the change or decision being made) (High, Medium, Low, No Impact) | Perception (how stakeholders perceive the change or decision being made) ( -, 0, +) | Issues & Concerns | Action Steps | Notes
The name of a group or name of an individual stakeholder. | The Organization that the stakeholder belongs to. | The job title of an individual stakeholder or functional area for a stakeholder group. | Unaware = Unaware of the CWS-CARES Implementation. Awareness = Becoming cognizant and developing a sense of appreciation for the goals of the CWS-CARES Implementation but current level significantly below the desired level Understanding = Internalizing the concepts and ideas and grasping the implications of the implementation. Buy-in = Agreement with the concepts and ideas presented and verbally expresses support to the CWS-CARES Implementation teams and to others in the organization. Commitment = Demonstrates commitment to the initiative. Individual feels responsible and accountable for its success. Individual can be leveraged as a spokesperson for the CWS-CARES Implementation. | Unaware = Unaware of the CWS-CARES Implementation. Awareness = Becoming cognizant and developing a sense of appreciation for the goals of the CWS-CARES Implementation but current level significantly below the desired level Understanding = Internalizing the concepts and ideas and grasping the implications of the implementation. Buy-in = Agreement with the concepts and ideas presented and verbally expresses support to the CWS-CARES Implementation teams and to others in the organization. Commitment = Demonstrates commitment to the initiative. Individual feels responsible and accountable for its success. Individual can be leveraged as a spokesperson for the CWS-CARES Implementation. | The level of influence over the success and/or perception of the CWS-CARES Implementation. High (H) -Holds significant decision-making power or represents a large group of people that will be affected by the CWS-CARES Implementation. These stakeholders are able to directly impact the project outcomes and can influence other stakeholders as well. Medium (M) - Holds moderate decision-making power or represents a smaller group of people that will be affected by the project. They are able to influence certain aspects of the project but not the overall outcome. Low (L) - Minimal decision-making power, financial or technical investment in the project, or represent a small group of people that will be affected by the project. These stakeholders have limited impact on the project outcomes. No Impact (N) - No impact on the project outcomes and is not actively involved in the CWS-CARES Implementation. Stakeholder just needs to be informed. | The degree of impact the CWS-CARES Implementation will have on the stakeholder. High (H) - Changes their job, requires attitude change and impacts their job long term; high personal concerns Medium (M) - Affects their job in part and has more short term impact and some long term possibly Low (L) - Little or no changes to their job and may be peripherally involved in change effort No Impact (N) - There are no impacts identified. | The perception the stakeholder is expected to have regarding the CWS-CARES Implementation. Negative (-) - This is a change that would not be favorably received; resistance is expected Neutral (0) - The CWS-CARES Implementation will not be viewed as a threat or added benefit Positive (+) - The CWS-CARES Implementation is a welcomed change | The key challenges with the stakeholder or primary concerns that stakeholder has regarding the CWS-CARES Implementation. | List any specific actions that need to be taken to effectively engage and manage each stakeholder or stakeholder group.